Work Plan for July – November 2013

Obey Creek Compass Committee

| Phases | Meeting Date | Topic | Outcomes | Materials |
| --- | --- | --- | --- | --- |
| Organizing | Wednesday, July 10th at 6:30 PM | Organizational Meeting - Committee charge and schedule – describe process and roles - Committee ground rules, facilitation - Existing conditions - resources - Workplan: Topics for future committee discussion | - Agreement on schedule - Agreement on ground rules - Identification of key issues for Committee discussion | - Existing conditions - Maps/handouts - Website materials |
| Public Workshop | Tuesday, August 13th at 7:00 PM? CH Public Library | Public workshop #1 - Existing Conditions - Principles for development - Identify main issues (transportation, use and form) | - Community identifies key issues for discussion on: Principles Options and trade offs Use and form Traffic Environment Economic impacts | - Background information - Technical team questions - Committee discussions |

| Project Proposal Development | Monday, August 12 | Special Topic Presentation by Victor Dover: Best Practices in New Projects | - Presentation is recorded and televised (and open to public attendance) | - Video - Powerpoint |
| --- | --- | --- | --- | --- |
|  | Monday, August 19 | Topic Meeting - Identify key topics for DA consideration in light of principles of 2020 - Prioritize key topics for discussion | - Discuss 2020 principles and refine based on public workshop - Identify focused points of discussion for topic meetings | - Principles from 2020 - Workshop outputs |
|  | Wednesday, September 18 | Topic Meeting |  |  |
|  | Wednesday, October 2 | Topic Meeting |  |  |

| Substance | Wednesday, September 4 | Topic Meeting Compare principles to initial concepts | - React to draft concepts | - Development team brings draft concept/s - Development team receives committee input - Drafts are posted |
| --- | --- | --- | --- | --- |
|  | Monday, October 14 | Topic Meeting |  |  |
|  | Monday and Tuesday, October 28-29 | Public Workshop on draft project proposal (concepts to final) |  |  |
|  | Monday, November 4 | Topic Meeting |  |  |
| Council | Council Meeting - Monday, November 25th at 7:00pm (same as central west) | Council meeting for consideration of the project proposal and exploratory phase recommendation |  |  |